## Gantt Chart
4
GANTT CHART
PROJECT TITLE |  | PrinterDynamix |  |  |  |  | ORGANIZATION NAME | [6 empty] | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE | [6 empty] | 2022-08-29
GL | Calen Sullivan
GM | John Waffenschmidt, Zed Fermon, Steve Cina, Hamil Dimapanat
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2022 |  |  |  |  | W2 9/12/2022 |  |  |  |  | W3 9/19/2022 |  |  |  |  | W4 9/26/2022 |  |  |  |  | W5 10/3/2022 |  |  |  |  | W6 10/10/2022 |  |  |  | W7 10/17/2022 | W8 10/24/2022 | W9 10/31/2022 | W10 11/7/2022 | W11 11/14/2022 | W12 11/21/2022 | W13 11/28/2022 | W14 12/5/2022
1 | Project Conception and Initiation
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.1.1 | Setting up Webex Account | All | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.2 | Setting up XAMPP / Unreal Engine | All | 2022-09-05 | 2022-09-12 | 7 | 100% | x | x | x | x | x
1.3 | Assigning Group Leader | Z.F. | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.4 |  |  |  |  | 0
1.5 |  |  |  |  | 0
1.6 |  |  |  |  | 0
2 | Design (Overall)
2.1 | Log-in System (Local) | C.S., S.C. | 2022-09-12 | 2022-10-07 | 0 | 100% | [5 empty] | x | x | x | x | x
2.1.2 | Functions to create and maintain PHP Session | S.C. |  |  |  | 100% | [15 empty] | x | x
2.1.3 | Function to validate user session prior to access granted | S.C. |  |  |  | 100% | [17 empty] | x
2.1.4 | Function to properly destroy the session | S.C. |  |  |  | 100% | [17 empty] | x
2.2 | Web Scraper (Program to go to Printer IPs) | Z.D, H.D. | 2022-10-03 | 2022-10-21 | 18 | 33% | [15 empty] | x | x | x | x | x |  |  | x | x | x | x
2.3 | Home Page & Website UI | J.W., H.D |  |  | 0 | 0% | [15 empty] | X |  |  |  |  | X | x
2.4 | Designing the User Database | S.C. | 2022-09-08 | 2022-09-08 | 0 | 100% |  |  |  | x | x |  |  | x | [7 empty] | x
2.5 | PHP functions for User CRUD | S.C. |  |  |  | 75% |  |  |  |  | x | [6 empty] | x | x | x | x | x
2.6 | Designing the Printer Database | Z.D., S.C. |  |  |  | 100% |  |  |  | x | x | [13 empty] | x
2.7 | PHP functions for Printer CRUD | C.S., S.C. | 2022-09-29 |  |  | 0%
2.8 | Build flowchart for log in | C.S., S.C. | 2022-09-19 | 2022-09-26 | #REF! | 100%
2.81 | Build overall flowchart | C.S.,S.C. | 2022-10-11 |  |  | 70%
2.5 | Analytics | C.S.,S.C. | 2022-10-07 |  | -44197 | 0%
2.6 | Use Case Diagram | Z.F.,C.S |  |  | 0 | 0%
2.7 | ADA Considered in Design | ALL |  |  | 0 | 0%
2.8 | Banner Logo across all webpages | J.W., H.D |  |  | 0 | 0%
2.9 | Login UI configured & design finished | C.S., S.C | 2022-09-12 | 2022-10-07 | 25 | 25% | [5 empty] | x | x | x | x | x |  |  |  | x | x
2.1 | PHP function to add printers to DB | C.S | 2022-10-03 | 2022-10-07 | 4 | 100% | [23 empty] | x
2.1.1 | Set up back up Git Repo | C.S. | 2022-10-03 | 2022-10-14 | 11 | 100% | [18 empty] | x
2.1.2 | Restructure GIT | S.C. | 2022-10-07 | 2022-10-14 |  | 100% | [25 empty] | x
2.1.3 | Import/Backup Scripts for SQL | S.C. | 2022-10-03 | 2022-10-07 | 4 | 100% |  |  |  |  | x | [13 empty] | x
2.1.4 | PHP Function to call Python Scraper on demand | S.C., Z.F. | 2022-10-03 | 2022-10-14 | 11 | 100% | [25 empty] | x | x
2.1.5 | Preliminary Python functions to query and/or add to DB | S.C., Z.F. | 2022-10-05 | 2022-10-05 | 1 | 100% | [24 empty] | x | x |  | x | x
3.6 | PHP function to display printer on a webpage | C.S. | 2022-10-03 | 2022-10-21 | 4 | 100% | [18 empty] | x | x | x | x | x | x
3 | Parts and Assembly (Weekly)
3.1 | User Functions for External Paper Inventory | C.S.,S.C. | 2022-10-14 | 2022-10-21 | 7 | 0%
3.2 | Build Website app draft | J.W., H.D. | 2022-10-03 | 2022-10-14 | 11 | 20% | [18 empty] | x |  |  |  |  | x
3.3 | Web Scraper ("Log Extractor") | Z.F. | 2022-10-03 | 2022-10-21 | 18 | 50%
3.32 | Fix scraper URL/model match function | Z.F. | 2022-10-11 | 2022-10-21 | 10 | 50%
3.33 | Add scraper parsing for color printers | Z.F | 2022-10-11 | 2022-10-21 | 10 | 0%
3.35 | Use Case Diagram | C.S. | 2022-10-14 | 2022-11-11 |  | 25%
3.4 | Populate Printer Tables Python Function | Z.F.,S.C. | 2022-10-03 | 2022-10-07 | 4 | 50%
3.5 | Add toner fields to display printer | C.S., S.C. | 2022-10-14 | 2022-10-21 | 7
3.7 | PHP function to pull printer info and add to CSV/DB | C.S. | 2022-10-14 | 2022-10-28 | 14
3.8 | Update Setup Scripts to include Python folder | S.C. | 2022-10-14 | 2022-10-21 | 7
3.9 | Edits to User DB (failed logon count field & boolean "is-locked") | S.C. | 2022-10-14 | 2022-10-21 | 7