## Gantt Chart
4
GANTT CHART
PROJECT TITLE |  | PrinterDynamix |  |  |  |  | ORGANIZATION NAME | [6 empty] | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE | [6 empty] | 2022-08-29
GL | Calen Sullivan
GM | John Waffenschmidt, Zed Fermon, Steve Cina, Hamil Dimapanat
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2022 |  |  |  |  | W2 9/12/2022 |  |  |  |  | W3 9/19/2022 |  |  |  |  | W4 9/26/2022 |  |  |  |  | W5 10/3/2022 |  |  |  |  | W6 10/10/2022 | W7 10/17/2022 | W8 10/24/2022 | W9 10/31/2022 | W10 11/7/2022 | W11 11/14/2022 | W12 11/21/2022 | W13 11/28/2022 | W14 12/5/2022
1 | Project Conception and Initiation
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.1.1 | Setting up Webex Account | All | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.2 | Setting up XAMPP / Unreal Engine | All | 2022-09-05 | 2022-09-12 | 7 | 100% | x | x | x | x | x
1.3 | Assigning Group Leader | Z.F. | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.4 |  |  |  |  | 0
1.5 |  |  |  |  | 0
1.6 |  |  |  |  | 0
2 | Design (Overall)
2.1 | Log-in System (Local) | C.S., S.C | 2022-09-12 | 2022-10-07 | 0 | 100% | [5 empty] | x | x | x | x | x
2.1.2 | Functions to create and maintain PHP Session | S.C. |  |  |  | 100% | [15 empty] | x | x
2.1.3 | Function to validate user session prior to access granted | S.C. |  |  |  | 100% | [17 empty] | x
2.1.4 | Function to properly destroy the session | S.C. |  |  |  | 100% | [17 empty] | x
2.2 | Web Scraper (Program to go to Printer IPs) | Z.D, H.D. | 2022-10-03 |  | -44193 | 33% | [15 empty] | x | x | x | x | x
2.3 | Home Page & Website UI | J.W., H.D |  |  | 0 | 0% | [15 empty] | X |  |  |  |  | X | x
2.4 | Designing the User Database | S.C. | 2022-09-08 | 2022-09-08 | 0 | 100% |  |  |  | x | x |  |  | x | [7 empty] | x
2.5 | PHP functions for User CRUD | S.C. |  |  |  | 75% |  |  |  |  | x | [6 empty] | x | x | x | x | x
2.6 | Designing the Printer Database | Z.D., S.C. |  |  |  | 100% |  |  |  | x | x | [13 empty] | x
2.7 | PHP functions for Printer CRUD | C.S., S.C | 2022-09-29 |  |  | 0%
2.8 | Build flowchart for log in | C.S., S.C | 2022-09-19 | 2022-09-26 | #REF! | 100%
2.5 | Analytics | C.S.,S.C. | 2022-10-07 |  | -44197 | 0%
2.6 | Use Case Diagram | Z.F.,C.S |  |  | 0 | 0%
2.7 | ADA Considered in Design | ALL |  |  | 0 | 0%
2.8 | Banner Logo across all webpages | J.W., H.D |  |  | 0 | 0%
2.9 | Login UI configured & design finished | C.S., S.C | 2022-09-12 | 10/7/2022 ? | #VALUE! | 25% | [5 empty] | x | x | x | x | x |  |  |  | x | x
2.1 | PHP function to add printers to DB | C.S | 2022-10-03 | 2022-10-07 | 4 | 100% | [23 empty] | x
2.1.1 | Set up back up Git Repo | C.S. | 2022-10-03 | 2022-10-14 | 11 | 100% | [18 empty] | x
2.1.2 |  |  |  |  | 0
2.1.3
2.1.4
2.1.5
3 | Parts and Assembly (Weekly)
3.1 | Import/Backup Scripts for SQL | S.C. | 2022-10-03 | 2022-10-07 | 4 | 100% |  |  |  |  | x | [13 empty] | x
3.2 | Build Website app draft | J.W., H.D., C.S. | 2022-10-03 | 2022-10-14 | 11 | 20% | [18 empty] | x |  |  |  |  | x
3.3 | Web Scraper ("Log Extractor") | Z.F. | 2022-10-03 | 2022-10-14 | 11 | 50%
3.31 | Preliminary Python functions to query and/or add to DB | S.C., Z.F. | 2022-10-05 | 2022-10-05 | 1 | 95% | [24 empty] | x
3.35 | PHP Function to call Python Scraper on demand | S.C., Z.F. | 2022-10-03 | 2022-10-14 | 11 | 50% | [25 empty] | x
3.4 | Populate Printer Tables Python Function | Z.F.,S.C. | 2022-10-03 | 2022-10-07 | 4 | 50%
3.6 | PHP function to display printer on a webpage | C.S. | 2022-10-03 | 2022-10-14 | 4 | 50% | [18 empty] | x | x | x | x | x | x
3.7 | Restructure GIT | S.C. | 2022-10-07 | 2022-10-14 |  | 100% | [25 empty] | x
3.8 | Use Case Diagram
There are two user tables, one in mysql db that covers accessing the DB, and a user table in printerdynamix that controls who is able to be logged on. They are in two different DBs so there is no conflict.
Set up relational database and output tables.