## Gantt Chart
GANTT CHART
PROJECT TITLE |  | PrinterDynamix |  |  |  |  | ORGANIZATION NAME | [6 empty] | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE | [6 empty] | 2022-08-29
GL | Zed Fermon
GM | John Waffenschmidt, Calen Sullivan, Steve Cina, Hamil Dimapanat
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2022 |  |  |  |  | W2 9/12/2022 |  |  |  |  | W3 9/19/2022 |  |  | W4 9/26/2022 | W5 10/3/2022 | W6 10/10/2022 | W7 10/17/2022 | W8 10/24/2022 | W9 10/31/2022 | W10 11/7/2022 | W11 11/14/2022 | W12 11/21/2022 | W13 11/28/2022 | W14 12/5/2022
1 | Project Conception and Initiation
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.1.1 | Setting up Webex Account | All | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.2 | Setting up XAMPP / Unreal Engine | All | 2022-09-05 | 2022-09-12 | 7 | 100% | x | x | x | x | x
1.3 | Assigning Group Leader | Z.F. | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.4 |  |  |  |  | 0
1.5 |  |  |  |  | 0
1.6 |  |  |  |  | 0
2 | Design
2.1 | Log-in System (AD view perms on campus & LDAP?) | C.S., S.C | 2022-09-12 | 10/7/2022 ? | 0 | [6 empty] | x | x | x | x | x
2.2 | Web Scraper (Program to go to Printer IPs) | Z.D, H.D. |  |  | 0
2.3 | Home Page & Website UI | J.W., H.D |  |  | 0
2.4 | Designing the User Database | S.C. | 2022-09-08 | 2022-09-08 | 0 | 95%
2.41 | PHP functions for User CRUD | S.C. |  |  |  | 25%
2.45 | Designing the Printer Database | Z.D., S.C. |  |  |  | 25%
2.46 | PHP functions for Printer CRUD | S.C. |  |  |  | 0%
2.5 | Analytics | C.S., S.C | 2022-10-07 |  | -44197
2.6 | Interviews/Meeting with Zed's boss | Z.F. |  |  | 0
2.7 | Use Case Diagram | Z.F. |  |  | 0
2.8 | ADA Considered in Design | ALL |  |  | 0
2.9 |  |  |  |  | 0
2.1 |  |  |  |  | 0
2.11 |  |  |  |  | 0
3 | Parts and Assembly
3.1 | Login UI configured & design finished | C.S., S.C | 2022-09-12 | 10/7/2022 ? | #VALUE! | 25% | [5 empty] | x | x | x | x | x |  | x | x
3.1.2 | Build flowchart for log in | C.S., S.C | 2022-09-19 |  | 0
3.2. | Banner Logo across all webpages |  |  |  | 0
3.2.1 |  |  |  |  | 0
3.3 |  |  |  |  | 0
3.3.1 |  |  |  |  | 0