## Gantt Chart
GANTT CHART
PROJECT TITLE |  | PrinterDynamix |  |  |  |  | ORGANIZATION NAME | [6 empty] | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE | [6 empty] | 2022-08-29
GL | Zed Fermon
GM | John Waffenschmidt, Calen Sullivan, Steve Cina, Hamil Dimapanat
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2022 |  |  |  |  | W2 9/12/2022 |  |  |  |  | W3 9/19/2022 |  |  |  |  | W4 9/26/2022 |  |  |  |  | W5 10/3/2022 | W6 10/10/2022 | W7 10/17/2022 | W8 10/24/2022 | W9 10/31/2022 | W10 11/7/2022 | W11 11/14/2022 | W12 11/21/2022 | W13 11/28/2022 | W14 12/5/2022
1 | Project Conception and Initiation
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.1.1 | Setting up Webex Account | All | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.2 | Setting up XAMPP / Unreal Engine | All | 2022-09-05 | 2022-09-12 | 7 | 100% | x | x | x | x | x
1.3 | Assigning Group Leader | Z.F. | 2022-09-05 | 2022-09-05 | 0 | 100% | x | x | x | x | x
1.4 |  |  |  |  | 0
1.5 |  |  |  |  | 0
1.6 |  |  |  |  | 0
2 | Design
2.1 | Log-in System (Local) | C.S., S.C | 2022-09-12 | 2022-10-07 | 0 | 0% | [5 empty] | x | x | x | x | x
2.1.2 | Functions to create and maintain PHP Session | S.C. |  |  |  | 0% | [15 empty] | x | x
2.1.3 | Function to validate user session prior to access granted | S.C. |  |  |  | 0% | [17 empty] | x
2.1.4 | Function to properly destroy the session | S.C. |  |  |  | 0% | [17 empty] | x
2.2 | Web Scraper (Program to go to Printer IPs) | Z.D, H.D. |  |  | 0 | 0% | [15 empty] | x | x | x | x | x
2.3 | Home Page & Website UI | J.W., H.D |  |  | 0 | 0%
2.4 | Designing the User Database | S.C. | 2022-09-08 | 2022-09-08 | 0 | 100% |  |  |  | x | x |  |  | x | [7 empty] | x
2.5 | PHP functions for User CRUD | S.C. |  |  |  | 75% |  |  |  |  | x | [6 empty] | x | x | x | x | x
2.6 | Designing the Printer Database | Z.D., S.C. |  |  |  | 100% |  |  |  | x | x | [13 empty] | x
2.7 | PHP functions for Printer CRUD | C.S., S.C | 2022-09-29 |  |  | 0%
2.8 | Build flowchart for log in | C.S., S.C | 2022-09-19 | 2022-09-26 | #REF! | 100%
2.5 | Analytics | C.S.,S.C. | 2022-10-07 |  | -44197 | 0%
2.6 | Interviews/Meeting with Zed's boss | Z.F. |  |  | 0 | 0%
2.7 | Use Case Diagram | Z.F. |  |  | 0 | 0%
2.8 | ADA Considered in Design | ALL |  |  | 0 | 0%
2.9 | Banner Logo across all webpages | J.W., H.D |  |  | 0 | 0%
2.1 | Login UI configured & design finished | C.S., S.C | 2022-09-12 | 10/7/2022 ? | #VALUE! | 25% | [5 empty] | x | x | x | x | x |  |  |  | x | x
2.11 |  |  |  |  | 0
3 | Parts and Assembly
3.1
3.2.1 | Import/Backup Scripts for SQL | SC |  |  | 0 | [5 empty] | x | [13 empty] | x
3.3 |  |  |  |  | 0
3.4 |  |  |  |  | 0
3.5 |  |  |  |  | 0