## Gantt Chart
GANTT CHART
PROJECT TITLE |  | PrinterDynamix |  |  |  |  | ORGANIZATION NAME |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE |  | 2022-08-29
| PM | Calen Sullivan
| Group Members | John Waffenschmidt, Zed Fermon, Steve Cina, Hamil Dimapanat
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2022 | W2 9/12/2022 |  | W3 9/19/2022 |  |  | W4 9/26/2022 |  | W5 10/3/2022 |  |  |  |  | W6 10/10/2022 |  |  |  | W7 10/17/2022 |  |  |  |  | W8 10/24/2022 |  |  |  |  | W9 10/31/2022 | W10 11/7/2022 |  |  |  |  | W11 11/14/2022 |  |  |  |  | W12 11/21/2022 |  |  |  |  | W13 11/28/2022 |  |  | W14 12/5/2022
1 | Project Conception and Initiation
1.1 | Setting up Github |  |  |  | 0
1.1.1 | Setting up Webex Account |  |  |  | 0
1.2 | Setting up XAMPP / Unreal Engine |  |  |  | 0
1.3 | Assigning Group Leader |  |  |  | 0
1.4 |  |  |  |  | 0
1.5 |  |  |  |  | 0
1.6 |  |  |  |  | 0
2 | Design
2.1 | UI | H.D., J.F. | 2022-10-03 | 2022-11-29 | 56 | 100% | [28 empty] | x | x |  |  |  | x |  | x |  | x |  |  | x | x
2.2 | PHP Functions | C.S., S.C. | 2022-10-03 | 2022-11-29 | 56 | 100% |  |  | x |  | x | x |  | x |  | x |  |  | x |  |  |  | x |  | x | x |  |  |  | x |  | x |  | x | x | [10 empty] | x | x |  |  |  | x | x
2.3 | Data Retrieval (scraper) | Z.F. | 2022-10-03 | 2022-11-29 | 56 | 100% | [8 empty] | x |  | x | x | x | x | x | x | x |  |  |  | x | x | x |  | x | x | x |  | x |  | x | x | x | x |  | x | x | x | [5 empty] | x
2.3.1 | Printer Database | Z.F, S.C | 2022-10-03 | 2022-11-29 | 56 | 100%
2.4 |  |  |  |  | 0 | [9 empty] | x |  | x | x | x | x | x | x | x |  |  |  | x | x | x |  | x | x | x |  | x |  | x | x | x | x |  | x | x | x
2.5 |  |  |  |  | 0
2.6 |  |  |  |  | 0
2.7 |  |  |  |  | 0
2.8 |  |  |  |  | 0
2.9 |  |  |  |  | 0
2.1 |  |  |  |  | 0
2.11 |  |  |  |  | 0
3 | Parts and Assembly
3.1 | Implement remove_printer.php | C.S., S.C. | 2022-11-07 | 2022-11-14 | 7 | 100% | [28 empty] | x | x | x |  |  |  |  | x |  |  |  | x |  |  | x | x
3.2 | Create a write up for about.php | C.S. | 2022-11-07 | 2022-11-14 | 7 | 100% | [28 empty] | x |  | x | x |  |  |  |  | x |  | x
3.3 | Implement update_external_stock.php | C.S. | 2022-11-07 | 2022-11-14 | 7 | 100% | [28 empty] | x |  |  | x
3.4 | Update display_printer | C.S. | 2022-11-07 | 2022-11-14 | 7 | 100% | [28 empty] | x |  |  | x | x |  | x | x
3.3 |  |  |  |  | 0
3.3.1 |  |  |  |  | 0